## TH0407
TH0407
Proposed
Grout lift | Base (m) | Top (m) | Number of mixes | Comments
NA | 99 | 97 |  | 1-2mm MGS filter sand
NA | 97 | 95 |  | Bentonite pellets
NA | 95 | 90 |  | Bentonite/ cement pellets
1 | 90 | 76.4 | 2 | Grout mix details below
2 | 76.4 | 56.8 | 4
3 | 56.8 | 50 | 1
4 | 50 | 25.97 | 5
5 | 25.97 | 15 | 2
6 | 15 | 2 | 2.6
7.5 x 24.75kg bags Geotherm X GR grout to 100L water / weight range to be between 1.67 and 1.72 sg
Should fill 6.75 m of hole per batch - figures on proposed assume 6 m to allow for some losses
Actual
Grout lift | Base (m) | Top (m) | Comments | Number of batches pumped | Grout weight SG | Start time | Finish Time | Recipe | Lift height per 100 L mix (m) | Dip inside install to top of 24" casing
| 99.513 | 97.07 | 1-2mm MGS filter sand
| 97.07 | 94.17 | Bentonite pellets
| 94.17 | 89.85 | Bentonite/ cement pellets
1 | 89.85 | 76.4 |  | 2 | 1.70 / 1.675 |  |  | first mix 7.5 bags Second mix 8 bags as still reading light after 7.5 bags more water added | 6.725
2 | 76.4 | 56.8 |  | 4 | 1.68 / 1.69 / 1.74 / 1.66 |  |  | 7.5 bags | 4.9 | 99.5
3 | 56.8 | 50.05 |  | 1 | 1.68 |  |  | 7.5 bags | 6.75 | 99.57
4 | 50.05 | 25.1 |  | 5 | 1.67 / 1.68 / 1.71 / 1.71 / 1.71 |  |  | 7.5 bags | 4.99
5 | 25.1 | 15.55 |  | 2 | 1.68/1.68 |  |  | 7.5 bags/100L, 7.5 bags/100L | 4.775 | 99.62
6 | 15.55 | 4.8 |  | 2.6 | 1.69/1.69/1.69 |  |  | 7.5 bags/106L, 7.5 bags/104L, 3.75 bags, 52L | 4.1346
7 | 4.8 | 2.1 | [5 empty] | 7.5 bags |  | 99.62
8 | 2.1 |  |  |  | Topped up with bucket mix
Note on E19: David Hetherington - BGS: Make a note of the expected TOC, include any details of losses encountered here
Note on G24: David Hetherington - BGS: first and last were big mixes so assumed 4