## TH0409
TH0409
Proposed
Grout lift | Base (m) | Top (m) | Number of mixes | Comments
NA | 101.1 | 100 |  | MGS filter gravel
NA | 100 | 97 |  | 1-2mm MGS filter sand
NA | 97 | 96 |  | Bentonite pellets
NA | 96 | 93 |  | Cement bentonite pellets
1 &2 | 93 | 79.7 | 3 | Grout mix details below
3 | 79.7 | 56.2 | 5
4 | 56.2 | 40.5 | 3
5 | 40.5 | 30 | 2
6 | 30 | 20 | 2
7 | 20 | 2 | 3.6
7.5 x 24.75kg bags Geotherm X GR grout to 100L water / weight range to be between 1.67 and 1.72 sg
Should fill 6.75 m of hole per batch - figures on proposed assume 6 m to allow for some losses
Actual
Grout lift | Base (m) | Top (m) | Comments | Number of batches pumped | Grout weight SG | Start time | Finish Time | Recipe | Lift height per 100 L mix (m) | Dip inside install to top of 24" casing
| 101 | 99.9 | MGS filter gravel
| 99.9 | 96.9 | 1-2mm MGS filter sand
| 96.9 | 95.27 | Bentonite pellets
| 95.27 | 92.36 | Bentonite/ cement pellets
1 | 92.36 | 83.4 |  | 2 | 1.71 / 1.71 |  |  | 7.5 bags | 4.48
2 | 83.4 | 79.7 |  | 1 | 1.67 |  |  | 7.5 bags | 3.7
3 | 79.7 | 56.23 | Tremie parted / left in hole | 5 | 1.68 / 1.67 / 1.73 / 1.67 |  |  | 7.5 bags | 4.694 | 99.97
4 | 56.23 | 42 | 2023-01-19 | 3 | 1.67/1.70/1.70 |  |  | 8 bags/105L, 7.5 bags/103L, 7.5 bags/107L | 4.7433 | 100.01
5 | 42 | 32.1 | 2023-01-23 | 2 | 1.68/1.68 |  |  | 7.5 bags/104L, 7.5 bags/104L | 4.95 | 100.05
6 | 32.1 | 22.4 | 2023-01-23 | 2 | 1.67/1.67 |  |  | 7.5 bags/104L, 7.5 bags/104L | 4.85
7 | 22.4 | 2.35 | 2023-01-24 | 4.5 | 1.67/1.69/1.68/1.69/1.69 |  |  | 7.5 bags/104L, 7.5 bags/104L, 7.5 bags/104L, 7.5 bags/104L, 3.75 bags/52L
8 | 2.35 |  |  |  | Topped up with bucket mix |  |  |  |  | 100
Note on K4: David Hetherington - BGS: Make a note of the expected TOC, include any details of losses encountered here
Note on E19: David Hetherington - BGS: Make a note of the expected TOC, include any details of losses encountered here
Note on E26: David Hetherington - BGS: shoe at 78.72 m, recovered 18 x joints of 2.46 m pipe (shorter sections) putting break at 44.28 m down, leaving 34.44 m in hole
Note on G26: David Hetherington - BGS: 4 lifts pumped first and last larger volumes so assumed volume pumped equates to 5 lift total