## TH0411
TH0411
Proposed
Grout lift | Base (m) | Top (m) | Number of mixes | Comments
NA | 100.2 | 99.5 |  | MGS filter gravel
NA | 99.5 | 97 |  | 1-2mm MGS filter sand
NA | 97 | 96 |  | Bentonite pellets
NA | 96 | 93 |  | Bentonite/ cement pellets
1 | 93 | 71.4 | 3.3 | Grout mix details below
2 | 71.4 | 52.2 | 4
3 | 52.2 | 42.2 | 3
4 | 42.2 | 17 | 5
5 | 17 | 2 | 3
6
7.5 x 24.75kg bags Geotherm X GR grout to 100L water / weight range to be between 1.67 and 1.72 sg
Should fill 6.75 m of hole per batch - figures on proposed assume 6 m to allow for some losses
Actual
Grout lift | Base (m) | Top (m) | Comments | Number of batches pumped | Grout weight SG | Start time | Finish Time | Recipe | Lift height per 100 L mix (m) | Dip inside install to top of 24" casing
| 99.8 | 99.45 | MGS filter gravel
| 99.45 | 97.1 | 1-2mm MGS filter sand
| 97.1 | 95.3 | Bentonite pellets
| 95.3 | 92.85 | Bentonite/ cement pellets
1 | 92.85 | 77.6 |  | 3.3 | 1.69 / 1.74 / 1.70 / 1.67 |  |  | 7.5 bags | 4.6212
2 | 77.6 | 71.4 |  | 1 | 1.67 |  |  | 7.5 bags | 6.2
3 | 71.4 | 52.2 | Tremie parted / left in hole | 4 | 1.74 / 1.69 / 1.71 / 1.70 |  |  | 7.5 bags | 4.8 | 100.05
4 | 52.2 | 42.2 |  | 3 | 1.67 / 1.70 / 1.71 |  |  | 7.5 bags | 3.3333 | 100.03
5 | 42.2 | 13.3 | Tremie parted / left in hole | 5 | 1.67/1.67/1.70/1.67/1.70 |  |  | 7.5 bags/105L for all batches | 5.45 | 99.98
6 | 13.3 | 3.6 |  | 2.2 | 1.69/1.69 |  |  | 7.5 bags/104L for both batches | 4.0791
7 | 3.6 | 2.1 | [5 empty] | 7.5 bags |  | 99.97
8 | 2.1 |  |  |  | Topped up with bucket mix
Note on K4: David Hetherington - BGS: Make a note of the expected TOC, include any details of losses encountered here
Note on E19: David Hetherington - BGS: Make a note of the expected TOC, include any details of losses encountered here
Note on E26: David Hetherington - BGS: base of tremie pipe at 71 m, broken section at 29.6 m (10 x joints recovered)
Note on E28: David Hetherington - BGS: Tremie pipe shoe at 22.18 m, top at 7.5 m (5 x 2.96 joints in the hole)
Note on K28: David Hetherington - BGS: 14.68 m of tremie displaces 12 l of fluid - deducted from total for second break 0.33 m