## TH0413
TH0413
Proposed
Grout lift | Base (m) | Top (m) | Number of mixes | Comments
NA | 101.8 | 100 |  | MGS filter gravel
NA | 100 | 97 |  | 1-2mm MGS filter sand
NA | 97 | 96 |  | Bentonite pellets
NA | 96 | 92 |  | Bentonite/ cement pellets
1 & 2 | 92 | 83.6 | 2 | Grout mix details below
3 | 83.6 | 60 | 5
4 | 60 | 40.35 | 4.5
5 | 40.35 | 20.4 | 4.5
6 | 20.4 | 15 | 1
7 | 15 | 2 | 2.6
7.5 x 24.75kg bags Geotherm X GR grout to 100L water / weight range to be between 1.67 and 1.72 sg
Should fill 6.75 m of hole per batch - figures on proposed assume 6 m to allow for some losses
Actual
Grout lift | Base (m) | Top (m) | Comments | Number of batches pumped | Grout weight SG | Start time | Finish Time | Recipe | Lift height per 100 L mix (m) | Dip inside install to top of 24" casing
| 101.7 | 100.03 | MGS filter gravel
| 100.03 | 97.1 | 1-2mm MGS filter sand
| 97.1 | 96 | Bentonite pellets
| 96 | 91.95 | Bentonite/ cement pellets
1 | 91.95 | 83.6 |  | 2 | 1.67 / 1.74 |  |  | 7.5 bags | 4.175 | 99.97
2 | 83.6 | 59.7 |  | 5 | 1.70 / 1.72 / 1.72 / 1.72 / 1.73 |  |  | 7.5 bags | 4.78 | 99.97
3 | 59.7 | 40.35 |  | 4.5 | 1.68 / 1.71 / 1.70 / 1.71 / 1.69 |  |  | 7.5 bags | 4.3
4 | 40.35 | 20.4 |  | 4.5 | 1.67/1.70/1.69/1,67/1.67 |  |  | 7.5 bags/105L, 7.5 bags/105L, 7.5 bags/105L, 7.5 bags/110L, 3.75 bags/52.5L | 4.4333 | 100.01
5 | 20.4 | 15.6 |  | 1 | 1.69 |  |  | 7.5 bags/104L | 4.8
6 | 15.6 | 5.8 |  | 2.6 | 1.67/1.69/1.68 |  |  | 7.5 bags 104L, 7.5 bags/104L, 3.75 bags/52L | 3.7692
7 | 5.8 | 2.6 | [7 empty] | 99.96
8 | 2.6 |  |  |  | Topped up with bucket mix
Note on K4: David Hetherington - BGS: Make a note of the expected TOC, include any details of losses encountered here
Note on E20: David Hetherington - BGS: Make a note of the expected TOC, include any details of losses encountered here