## TH0419 final design 30-06-23
Backfill design for Waterloo 401 MLS TH0419
Note that all depth measurements are referenced to the 24" Boode casing top
Consumption
| Geotherm GX grout | 42.25
| Bentonite pellets (Mikolit 300) | 57.25
| 1-2mm filter sand | 54
| 4-10mm MGS gravel | 7.25
| 6-10mm Derby gravel | 13.25
| sharp sand | 2
Assumed Borehole diameter (mm) | Adjusted port depth (Solinst sheet) in ft | Final adjusted port depth in m bct | Approx. Port Depth in m | Large Fracture Depths (m bct) red= class 3 | Backfill depths (m bct) | Start Time | End Time | Bags Used | Dip Check (m) | Comments
[5 empty] | Geotherm GX grout from 12.0 to 0.5m | 2023-07-06 19:00 | 2023-07-07 00:37 | 42.25 |  | Topped up at later date
[5 empty] | 1m of sharp sand from 13.0 to 12.0m | 2023-07-06 16:40 | 2023-07-06 16:56 | 2 | 12.15
[5 empty] | 2.0 m Bentonite pellets (Mikolit 300) from 15.0 to 13.0 m | 2023-07-06 16:00 | 2023-07-06 16:32 | 2.75 | 13.05
[5 empty] | 0.5m of 1-2mm filter sand from 15.5 to 15.0 m | 2023-07-06 14:35 | 2023-07-06 14:50 | 1 | 14.93
|  |  |  | 16.5, 17.0, 17.9 | 3.0m of 6-10mm Derby gravel from 18.5 to 15.5 m | 2023-07-06 14:20 | 2023-07-06 14:34 | 4.5 | 15.58
| 65 | 19.812 | 16.5 | 19.2 | 2.5m of 1-2mm sand filter pack from 21.0 to 18.5 m | 2023-07-06 14:15 | 2023-07-06 14:20 | 4 | 18.43
200mm |  |  |  | 23.5 | 2.5m Bentonite pellets (Mikolit 300) from 23.5 to 21.0 m | 2023-07-06 13:30 | 2023-07-06 13:58 | 6 | 20.86
| 82.5 | 25.146 | 24.5 |  | 3.0 m of 1-2mm sand filter pack from 26.5 to 23.5 m | 2023-07-06 13:10 | 2023-07-06 13:30 | 5 | 23.4
|  |  |  | poss 26.9, 27.4 | 1.5 m of 6-10mm Derby gravel from 28.0 to 26.5 m | 2023-07-06 13:00 | 2023-07-06 13:07 | 3 | 23.35
[5 empty] | 0.5m of 1-2mm filter sand from 28.5 to 28.0 m | 2023-07-06 12:50 | 2023-07-06 12:58 | 1 | 27.95
|  |  |  | 29.7 | 3.0m Bentonite pellets (Mikolit 300) from 31.5 to 28.5 m | 2023-07-06 12:20 | 2023-07-06 12:50 | 4 | 28.57
|  |  | 36.5 |  | 0.5m of 1-2mm sand filter pack from 32.0 to 31.5 m | 2023-07-06 11:59 | 2023-07-06 12:20 | 1 | 31.37
|  |  |  | 32.2, 32.5, 32.8, 33.0, 33.7, 34.4 | 3.0 m of 6-10mm Derby gravel from 35.0 to 32.0 m | 2023-07-06 11:30 | 2023-07-06 11:52 | 5.75 | 32
| 120 | 36.576 |  |  | 3.0m of 1-2mm filter sand from 38.0 to 35.0 m | 2023-07-06 10:30 | 2023-07-06 11:01 | 6 | 35.15
|  |  |  | 44.2, poss 48.0 | 11.0m Bentonite pellets (Mikolit 300) from 49.0 to 38.0 m | 2023-07-06 03:10 | 2023-07-06 10:21 | 14.25 | 38.04 | Break from 03:20 to 08:00
| 167.5 | 51.054 | 50 | none | 4.0 m of 1-2mm sand filter pack from 53.0 to 49.0 m | 2023-07-06 02:30 | 2023-07-06 03:10 | 7 | 48.9
[5 empty] | 3.0 m Bentonite pellets (Mikolit 300) from 56.0 m to 53.0 m | 2023-07-06 01:10 | 2023-07-06 02:30 | 4.5 | 53.03
| 190 | 57.912 | 59 | 56.8 | 3.8 m of 1-2mm sand filter pack from 59.8 to 56.0 m | 2023-07-05 23:15 | 2023-07-06 01:10 | 6 | 56.1
|  |  |  | 61.3 | 3.0 m of 4-10mm MGS gravel from 62.8 to 59.8 m | 2023-07-05 20:45 | 2023-07-05 23:15 | 5 | 59.8
[5 empty] | 0.5m of 1-2mm filter sand from 63.3 to 62.8 m | 2023-07-05 20:15 | 2023-07-05 20:45 | 1 | 62.75
[5 empty] | 3.2m Bentonite pellets (Mikolit 300) from 66.5 to 63.3 m | 2023-07-05 16:28 | 2023-07-05 20:15 | 6.25 | 63.25
| 224.5 | 68.4276 | 68.5 | none | 4 m of 1-2mm sand filter pack from 70.5 to 66.5 m | 2023-07-05 14:54 | 2023-07-05 16:08 | 6.5 | 66.56
|  |  |  | 71.1 | 4.5m Bentonite pellets (Mikolit 300) from 75.0 to 70.5 m | 2023-07-05 12:55 | 2023-07-05 14:52 | 6.25 | 70.35
| 253 | 77.1144 | 76.5 |  | 4.0 m of 1-2mm sand filter pack from 79.0 to 75.0 m | 2023-07-05 11:10 | 2023-07-05 12:50 | 6.5 | 74.97
|  |  |  | 78.1, 79.5, 80.0 | 2.0 m of 4-10mm MGS gravel from 81.0 to 79.0 m | 2023-07-05 10:35 | 2023-07-05 11:07 | 2.25 | 79.1
[5 empty] | 0.5m of 1-2mm filter sand from 81.5 to 81.0 m | 2023-07-05 10:09 | 2023-07-05 10:30 | 1 | 80.93
[5 empty] | 8.5m Bentonite pellets (Mikolit 300) from 90.0 to 81.5 m | 2023-07-05 01:00 | 2023-07-05 10:07 | 11 | 81.58 | Break from 03:20 to 07:55
| 303.5 | 92.5068 | 92.5 |  | 5 m of 1-2mm sand filter pack from 95.0 to 90.0 m | 2023-07-04 21:00 | 2023-07-05 01:00 | 8 | 90.1
[5 empty] | 2.5m Bentonite pellets (Mikolit 300) from 97.5 to 95.0 m | 2023-07-04 19:30 | 2023-07-04 21:00 | 2.25 | 95.05
[5 empty] | 4-10mm MGS gravel from base to 97.5 m | N/A
MLS Base plug at 97m